Minutes, UK CMS EE Meeting, 22.1.2003

1) DaveC	E0’

Proposed sequence:

### Jan/Feb	in UK

Backplate prepared

SC0 umbilical prepared with RG179 cable

Feb		Shipment to CERN

SC0 and SC1

Backplate etc + outer outer cooling box

50 Stephenson preamps

HT units + 200m HT cable

LV supply for Stephenson preamps

F.O. monitoring diffuser, PN diodes

Thermisters?

March	Rebuild E0’ in bldg 11

Readout

Stephenson preamps to CAMAC OPAL ADCs to PC

Use Labview

Setup data storage etc

Study/check SM0/1 (light pulses, charge inj, noise)

April			Continue

May/July		Install ECAL electronics

4 motherboards

6 cooling spines (take those for basket 2?)

VFE as available

FE with Xilinx chip

Digital fibre readout to converted ROSE10 ULR

August/Sep		Move to H4

E0’ with ECAL cooling and ECAL electronics

Notes of 6.12.2002 meeting with B Ille, M Hansen, R Benetta, O Teller at http://hepwww.rl.ac.uk/CMSecal/E0'/E0prime.doc

ACTIONS

1) Laury		SC01/2 umbilicals, HV pcbs, new connectors after discussion with Tony

2) DaveC	Ship all ‘good’ FNUF (~40) xtals from 2001, from CERN=>RAL=> IC Xtal lab

3) DaveC	Contact Mossiere for ancilliary equipment for cooling spines

4) DaveC	Contact Lubo for motherboards

5) DaveC	Contact Jim Grahl for light to light system for E0’/12 way yellow ribbon

6) DaveC	Contact Saclay, 75 porte ferrules for the monitoring fibres

2) Bob	General CMS/ECAL situation

Answer from BERN expected before April RRB concerning Swiss funding

ECAL cost at 111MCF, with matching funding.

Rely on what Russians can do for us to be fully covered.

Barrel FPPA appears OK, noise less than 15k e- (limitd by test kit)

0.25(m preamp: submission in Feb 2003, 6 weeks for delivery (note Tracker 0.25(m yield problems)

Xtal production.	Cutting/annealing problems with bigger boules

Xtal production. Need	65mm boules for 2 EB xtals

75mm boules for 2 EE xtals

85mm boules for 4 EB xtals

Decision to jump to addressing problems of 85mm boules now.

100 EE xtals in 2003, 50 in March, 50 in April.

3) Justin	TD in 2003

Q1/Q2	Tony, mechatronics on back of Dee

Q3/Q4	John, mechanical drawings/layout for the mechatronics

By spring 2005, a bare Dee will be waiting for mechatronics

Need mechatronics done by start 2004

John	Major mechanics, OJEC, 12 May tender request sent out

1 Oct, award contract

7 Feb, FDR at RAL, RF, BP, PS (ring flange, back plate, pos. spacers)

20 Feb, FDR at CERN, ditto + Env. Screen + partial PS

Justin	Thermal – duct cooling, selection of polymers

Structural – Dee edge deflaections, bumpstop

Project management, costings, progress

4) Ken		New group at CERN joining EE, Lucy Linssen, TA1(mechanical)

1-2 draftsmen + number of mechanical technicians. No real design engineer.

Lucy	full responsibility for	Dee assy lab, Dee loader, mods to OPAL frames,

Dee rotator, Dummy Dees, Installation and platforms, E0’ table at H4.

Ken	linkperson to Lucy with RAL TD, Austin and Herve,

EE fibres, trigger knitting and contact to Jim Grahl for optical R/O.

Bare (BP+SCs) Dee assy lab likely to be bldg 904 on Prevessin site

Only has 10T crane vs 12T for Dee+misc.

Wolfgang Funk – ECAL services supremo, EB+EE+ES

Dieter Schintzel – ECAL installation supremo

5) Bruce	4k VPTs in 2003, 40/day = 100 days of running

4th row of 8 cans a possibility.

Database for SC assembly – starting to prepare.

6) Helen		Bristol in 2003

testbeam major input – agree to be E0’ testbeam coordinator

with test beam team of Dan holmes (was at H4 in 2002), Vince, Dave Cussans

David Bailey - Fast Monte Carlo

Dave Cussans - VPT irradiation writeup, HT filter n-irradiation at Minnesota

7) DaveB	IMPERIAL, in 2003

Xtal lab, HV failure – new HV, previous data was OK

Uniformising xtals for next 2 SCs, xtals urgently wanted from CERN.

Matt Ryan – look at new 2003 xtals asap

By 1st June want to say FNUFs/irradiations OK, for full xtal order to proceed

Imperial		Short time irradiation studies using Brunel spectrophotometer

Involvment (+ChrisS?) with test beam preparation and shifts.

ACTIONS

DaveC to contact F. Nessi to ensure rapid ACCOS throughput of xtals at CERN

8) Peter		Brunel in 2003

4T VPT work continues. Trying for higher throughput.

Multiple VPT torpedo development, but proceeds slowly through magnet.

Faceplates + study of long term reverse annealing issue.

Materials irradiation studies.

HT filter irradiation studies at rate, at rate after 10yr dose, ( VPT, with frequency scan.

Omar Sharif – new ECAL RA will contribute to test beam + VPTs

Physics